## Sheet1
Team Members: The Night Owlers
| First Name | Last Name | Student ID
| Theebika | Thiyagaraja Iyer | 40191001
| Shami Ivan | Senga | 40228447
| Angru | Li | 40123754
| Jutipong | Puntuleng | 40080233
| Ryan | Mazari | 40241379
Sprint 1
Date | Members name | Task | Hour spent
2024-02-05 | Jutipong Puntuleng | Plan and Create wireframe | 2hr
2024-02-06 | Jutipong Puntuleng | Continue creating wireframe | 30min
2024-02-07 | Jutipong Puntuleng | Make project approach | 2 hr
2024-02-08 | Jutipong Puntuleng | Continue making project approach | 2.5hrs
2024-02-09 | Jutipong Puntuleng | Continue making project approach | 1hr
2024-02-10 | Jutipong Puntuleng | Continue making project approach | 1hr
2024-02-10 | Jutipong Puntuleng | Make README.md | 3hrs
2024-02-11 | Jutipong Puntuleng | Continue making README.md | 1hr
2024-02-11 | Jutipong Puntuleng | Create user stories | 2.5hrs
2024-02-06 | Angru Li | write the Integration and Interoperability first draft | 3hrs
2024-02-09 | Angru Li | Write project overview | 2 hrs
2024-02-09 | Angru Li | Write user stroies | 3.5 hrs
2024-02-07 | Angru Li | continue to write user stories | 1.5 hrs
2024-02-10 | Angru Li | revise project overveiw | 1hr
2024-02-06 | Theebika Thiyagaraja Iyer | Work on wirefram | 30 min
2024-02-07 | Theebika Thiyagaraja Iyer | Work on wireframe + search for ideas | 1hr
2024-02-08 | Theebika Thiyagaraja Iyer | Research for project approach | 30 min
2024-02-10 | Theebika Thiyagaraja Iyer | Create User Stories for CRUD vehicles,users and split them | 3hrs
2024-02-11 | Theebika Thiyagaraja Iyer | Write/formatting Meeting minutes + Team members and roles and upload on github | 2hrs
2024-02-12 | Theebika Thiyagaraja Iyer | Review everything and create log file | 2hrs
2024-02-03 | Shami Ivan Senga | Meeting preparation | 5 min
2024-01-03 | Shami Ivan Senga | Meeting | 30min
2024-02-07 | Shami Ivan Senga | Work on project setup(installing next js) | 1hr
2024-01-06 | Shami Ivan Senga | Project setup on github | 3hrs
2024-01-07 | Shami Ivan Senga | Work on github projects | 2hrs
2024-01-06 | Shami Ivan Senga | Work on section 3(Technology) | 5hrs
2024-02-07 | Shami Ivan Senga | Meeting | 2hrs
2024-01-06 | Shami Ivan Senga | Work section 3 Technology | 4hrs
2024-02-12 | Shami Ivan Senga | Work on project approach | 3hrs
2024-02-13 | Shami Ivan Senga | Work on project setup(github projects) | 5hrs
2024-02-07 | Ryan Mazari | Brainstorming User Stories (how to divide them, which order to list them) | 4hrs
2024-02-08 | Ryan Mazari | Wrote 6 user stories | 6hrs
2024-02-09 | Ryan Mazari | Redid the user stories in accordance to Lecture Week 4 before Lab Session on Friday | 3hrs
2024-02-10 | Ryan Mazari | After receiving feebacks during Lab Session, had to again modify user stories | 4hrs
2024-02-11 | Ryan Mazari | Continued writing user stories + linked them to tasks | 5hrs
2024-02-12 | Ryan Mazari | Finished user stories, only linked user stories to tasks | 2hrs