## Main
Team Name: The Night Owlers
First Name | Last Name | Student ID
Theebika | Thiyagaraja Iyer | 40191001
Shami Ivan | Senga | 40228447
Angru | Li | 40123754
Jutipong | Puntuleng | 40080233
Ryan | Mazari | 40241379

## Theebika Thiyagaraja Iyer
Sprint 1
Date | Members name | Task | Hour spent | Start time | End time
2024-02-06 | Theebika Thiyagaraja Iyer | Work on wirefram | 30 min | 13:00 | 13:30
2024-02-07 | Theebika Thiyagaraja Iyer | Work on wireframe + search for ideas | 1hr | 15:30 | 16:30
2024-02-08 | Theebika Thiyagaraja Iyer | Research for project approach | 30 min | 21:15 | 21:45
2024-02-10 | Theebika Thiyagaraja Iyer | Create User Stories for CRUD vehicles,users and split them | 3hrs | 20:00 | 23:00
2024-02-11 | Theebika Thiyagaraja Iyer | Write/formatting Meeting minutes + Team members and roles and upload on github | 2hrs | 10:00 | 12:00
2024-02-12 | Theebika Thiyagaraja Iyer | Review everything and create log file | 2hrs | 18:00 | 20:00
Sprint 2
Date | Members name | Task | Hour spent | Start time | End time
2024-02-26 | Theebika Thiyagaraja Iyer | Working on wireframe and organizing the frames #94 | 1 hour | 15:00 | 16:00
2024-02-27 | Theebika Thiyagaraja Iyer | Creating wireframe task 1.2.1 #137 | 2 hours | 16:00 | 18:00
2024-03-01 | Theebika Thiyagaraja Iyer | Working on wireframe task 5.2.1 #94 and complete it | 2 hours | 15:00 | 17:00
2024-03-03 | Theebika Thiyagaraja Iyer | Start implement task 1.2.1 | 2 hours | 19:00 | 21:00
2024-03-04 | Theebika Thiyagaraja Iyer | Implement task 1.2.2,1.2.3,1.2.4 and use tailwind for styling | 7 hours | 12:00 | 19:00
2024-03-05 | Theebika Thiyagaraja Iyer | implement adding vehicles and connecting to db and task 1.2.6 | 4 hours | 16:00 | 20:00
2024-03-05 | Theebika Thiyagaraja Iyer | Working on database for adding vehicles task 5.2.2, 5.2.3 | 5 hours | 14:00 | 19:00
2024-03-06 | Theebika Thiyagaraja Iyer | Implementing adding vehicles and work on 5.1.3 | 1 hour | 1:00 | 2:00
2024-03-07 | Theebika Thiyagaraja Iyer | Adding User stories and tasks for Sprint 3 for Branch and Checkout and assign for each member | 2 hours | 14:00 | 16:00
2024-03-08 | Theebika Thiyagaraja Iyer | Link the pages and fix some issues | 2 hours | 22:00 | 0:00
2024-03-09 | Theebika Thiyagaraja Iyer | Work on meeting minutes and link the pages together | 3 hours | 17:00 | 20:00
2024-03-10 | Theebika Thiyagaraja Iyer | Work on meeting minutes, closing issues on github, go over the grading rubric and review documentation | 2 hours | 17:00 | 19:00
2024-03-11 | Theebika Thiyagaraja Iyer | Complete Meeting minutes and upload on github, add priority and risks for tasks for Sprint 3, review if everything is completed | 3 hours | 11:00 | 14:00
2024-03-11 | Theebika Thiyagaraja Iyer | Fixing merging issues, complete log file, review github, close all pull requests, close issues | 3 hours | 20:00 | 23:00
Sprint 2
Date | Members name | Task | Hour spent | Start time | End time
2024-03-19 | Theebika Thiyagaraja Iyer | Write meeting min | 30 min | 16:00 | 16:30
2024-03-20 | Theebika Thiyagaraja Iyer | Acceptance test for User story 7 | 1 hour | 19:00 | 20:00
2024-03-20 | Theebika Thiyagaraja Iyer | Start implementing task 7.1 worked on Search branch | 2 hours | 23:00 | 1:00
2024-03-21 | Theebika Thiyagaraja Iyer | Fix and complete Task 7.1 + close issues and add comments | 1.5 hours | 17:00 | 18:30
2024-03-21 | Theebika Thiyagaraja Iyer | Adding Acceptance Test for User story 8 | 2 hours | 21:00 | 23:00
2024-03-21 | Theebika Thiyagaraja Iyer | Task 9.1 and Task 9.2 worked on branch Checkout | 4 hours | 23:00 | 3:00
2024-03-22 | Theebika Thiyagaraja Iyer | Complete Acceptance stories and fix AT for User story 7 and 8 | 1.5 hours | 14:00 | 15:30
2024-03-22 | Theebika Thiyagaraja Iyer | UML Diagram planning for User Story Branch | 30 min | 17:45 | 18:15
2024-03-23 | Theebika Thiyagaraja Iyer | Fixing meeting min | 1 hour | 19:00 | 20:00
2024-03-24 | Theebika Thiyagaraja Iyer | Rework on Meeting Min, Review All Documentation: Sprint Planning 4 + Activity Diagram | 2 hours | 23:00 | 1:00

## Shami Ivan Senga
Sprint 1
Date | Task | Hour spent | Start time | End time
2024-02-03 | Meeting preparation | 5 min | 11:00 | 11:05
2024-02-07 | Work on project setup(installing next js) | 1hr | 30 min | 30 min
2024-01-06 | Project setup on github | 3hrs | 12:00 | 3:00
2024-01-07 | Work on github projects | 2hrs | 7:00 | 9:00
2024-01-06 | Work on section 3(Technology) | 5hrs | 9:00 | 23:00
2024-01-06 | Work section 3 Technology | 4hrs | 18:00 | 22:00
2024-02-11 | Work on project approach | 3hrs | 17:00 | 7:00
2024-02-12 | Work on project setup(github projects) | 5hrs | 10:00 | 13:00
Sprint 2
Date | Task | Hour spent | Start time | End time
2024-02-26 | Sketch wireframe for registration Task 4.1.1 #77 and for admin dashboard task 4.2.1 #83 | 2 hours | 19:00 | 21:00
2024-02-27 | Sketch wireframe for editing/modifying fields Task 4.3.4 #151 and 1.3.1 #143 | 3 hours | 7:00 | 10:00
2024-02-28 | Integrate frontend logic and the backend logic, task 1.2.4 #140 | 4.5 hours | 12:00 | 16:30
2024-02-29 | Task 5.1.4 #96 set yp mongoDb schema for user | 3 hours | 10:00 | 13:00
2024-03-01 | Implement backend logic | 6 hours | 14:00 | 20:00
2024-03-02 | Implement task 5.2.3 #152 | 4 hours | 19:00 | 23:00
2024-03-02 | Task 1.3.4 and 1.3 5 #146 and #147 set up API and handle loading states and erros | 3 hours | 11:00 | 14:00
2024-03-02 | Create customer account user story 4.1, tasks 4.1.1-4.1.6 #77,78,79,80,81 | 4 hours | 16:00 | 20:00
2024-03-04 | Continuation of customer account | 3 hours | 19:00 | 22:00
2024-03-05 | set up mongodb for users task 5.1.4 #96 | 2 hours | 9:00 | 11:00
2024-03-06 | CRUD for users and set up MongoDB for reservation #59 task 2.1.6 | 3.5 hours | 9:30 | 12:00
2024-03-07 | continuation for CRUD users | 4.5 hours | 17:00 | 21:30
2024-03-08 | Task 5.3.2 - 5.3.6 #157,158,161 Validation check for vehicle information and ensure responsiveness | 6 hours | 15:00 | 21:00
2024-03-09 | Authentication logic for login, signup #82 | 4 hours | 20:00 | 0:00
2024-03-10 | Working on implementing backend logic for reservation and styling the pages | 5 hours | 9:00 | 14:00
2024-03-11 | Working on implementing CRUD reservation | 3.5 hours | 16:30 | 20:00
Sprint 3
Date | Task | Hour spent | Start time | End time
2024-03-13 | reservation : setup post routes for making reservations | 1 | 3:54 | 4:54
2024-03-15 | dispaying button if user is signed in(button changes, depending on the session) | 1 | 9:00 | 10:00
2024-03-18 | Feature(checkin) Adding database call to get reservation by Id and update a reservation given it's id | 1 | 17:30 | 19:00
2024-03-18 | refactoring to go from ts to js | 0 | 22:00 | 22:30
2024-03-19 | Fixing a session bug. The session gets cached and if the user signs out and reload, he's signed in. | 3 | 11:00 | 14:30
2024-03-21 | Feature (location) : Add database function to add remove update | 0.5 | 7:30 | 8:00
2024-03-21 | Database redesign to contain locations and branches | 2 | 17:30 | 20:00
2024-03-22 | Feat : Add Api endpoints for reservation | 1 | 9:00 | 10:00
2024-03-22 | Feature(location) : Add backend function to filter vehicles based on locations | 3 | 11:00 | 14:30
2024-03-23 | Fix (location) : Write function to get the overlay of vehicles | 0.5 | 7:30 | 8:00
2024-03-23 | Fix build error : casing error caused byt vercel deployement | 1 | 9:00 | 10:00
2024-03-24 | Style Admin page : Add modals for creating cars | 2 | 17:30 | 20:00
2024-03-25 | Style Admin page : Add modal for creating new location | 2 | 17:30 | 20:00
2024-03-25 | Style (Login page) : Redesign the login page include signup | 2 | 6:00 | 8:30

## Angru Li
Sprint 1
Date | Members name | Task | Hour spent | Start time | End time
2024-02-06 | Angru Li | write the Integration and Interoperability first draft | 3hrs | 10:00 | 13:00
2024-02-09 | Angru Li | Write project overview | 1 hrs | 10:00 | 11:00
2024-02-09 | Angru Li | Write user stroies | 2 hrs | 20:00 | 22:00
2024-02-07 | Angru Li | continue to write user stories | 1.5 hrs | 14:30 | 16:00
2024-02-10 | Angru Li | revise project overveiw | 1hr | 10:00 | 11:00
2024-02-09 | Angru Li | revise project overveiw | 1 hrs | 15:00 | 16:00
2024-02-08 | Angru Li | Write user stroies | 1.5 hrs | 20:00 | 21:30
Sprint 2
Date | Members name | Task | Hour spent | Start time | End time
2024-02-26 | Angru Li | Learn the basic function of a node js,work on the test file for connecting database | 2hr | 10:00 | 12:00
2024-02-27 | Angru Li | Try to set the dabase system | 1hr | 22:00 | 23:00
2024-02-28 | Angru Li | Set the database system and let it connect with our project | 2hr | 10:00 | 12:00
2024-03-02 | Angru Li | Work on the vehicle's database Crud part (mongo db) | 2hr | 17:00 | 19:00
2024-03-03 | Angru Li | convert the user story to task (9.4)(9.4.1),(9.4.2)(9.4.3)(9.4.4) | 1hr | 18:00 | 19:00
2024-03-04 | Angru Li | Set the database system and let it connect with our project | 1hr | 18:00 | 19:00
2024-03-05 | Angru Li | Convert the user story to task (9.5)(9.5.1)(9.5.2)(9.5.3)(9.5.4) | 1hr | 17:00 | 18:00
2024-03-07 | Angru Li | FIx the issue for the route file | 5hr | 10:00 | 15:00
2024-03-09 | Angru Li | Work on the vehicle's database Crud part (mongoose) | 5hr | 22:00 | 3:00
2024-03-10 | Angru Li | Try to imply the parameter from the database to webpage, create a functional api for it | 4hr | 19:00 | 23:00
2024-03-11 | Angru Li | Working on the route and fix the issue I face | 3hr | 15:00 | 18:00
2024-03-11 | Angru Li | Imply the parameter from the database to vehicle detail page successfully | 2hr | 19:00 | 21:00
Sprint 3
Date | Members name | Task | Hour spent | Start time | End time
2024-03-15 | Angru Li | Learn how to use the access control and work on how to implement handing to go back to the dashboard(9.5) | 2.5hr | 13:00 | 14:30
2024-03-17 | Angru Li | Try to implement logic to update reservation status and work on"update reservation when user check out"(9.4) | 2.5hr | 20:00 | 22:00
2024-03-18 | Angru Li | Adding more parameter for the database when working on task 9.4 | 1hr | 16:00 | 17:30
2024-03-19 | Angru Li | Revise CSV file to add picture for each vehicle | 1hr | 17:00 | 18:00
2024-03-20 | Angru Li | Adding more parameter for the database | 1.5hr | 20:00 | 22:00
2024-03-21 | Angru Li | Revise CSV file to add picture for each vehicle | 1hr | 21:00 | 22:00
2024-03-22 | Angru Li | Revise CSV file to add picture for each vehicle | 1hr | 20:00 | 21:00

## Jutipong Puntuleng
Sprint 1
Date | Members name | Task | Hour spent | Start time | End time
2024-02-05 | Jutipong Puntuleng | Plan and Create wireframe | 2hrs | 10:00 | 12:00
2024-02-06 | Jutipong Puntuleng | Continue creating wireframe(not finish) | 30min | 11:00 | 11:30
2024-02-07 | Jutipong Puntuleng | Research on project approach | 1hr 15min | 17:00 | 18:15
2024-02-08 | Jutipong Puntuleng | Make project approach | 45min | 18:15 | 19:00
2024-02-08 | Jutipong Puntuleng | Continue making project approach | 2hrs 30min | 10:00 | 12:30
2024-02-09 | Jutipong Puntuleng | Continue making project approach | 1hr | 21:00 | 22:00
2024-02-10 | Jutipong Puntuleng | Finish project approach | 1hr | 12:00 | 14:00
2024-02-10 | Jutipong Puntuleng | Make README.md | 2hrs 30min | 14:30 | 17:00
2024-02-10 | Jutipong Puntuleng | Modify project apporach | 30min | 10:00 | 10:30
2024-02-11 | Jutipong Puntuleng | Finish making README.md | 1hr | 10:30 | 11:30
2024-02-11 | Jutipong Puntuleng | Create sub user stories and link it to task | 2hrs 30min | 14:30 | 17:00
Sprint 2
Date | Members name | Task | Hour spent | Start time | End time
2024-02-26 | Jutipong Puntuleng | Start creating wireframe for the Task 6.4.1 and 2.31 and 6.3.1 (#114 & #123 & #112) | 2hrs | 14:45 | 4:45
2024-02-27 | Jutipong Puntuleng | Creating the wireframe for the Task 2.1.1 and 2.2.1 and 6.1.1 (#55 & #72 & #103) | 2hrs | 15:30 | 17:30
2024-02-28 | Jutipong Puntuleng | Creating the wireframe for the Task 2.2.2 and 6.2.1 and 4.41(#73 & # 107 & #118) | 1hrs | 15:30 | 16:30
2024-03-01 | Jutipong Puntuleng | Start implement the Reservation form page for Task 2.1.2 and 2.1.3. (#56 & # 57) | 1hrs 30min | 9:00 | 22:30
2024-03-01 | Jutipong Puntuleng | Continue implement the Reservation form page for Task 2.1.2 and 2.1.3. (#56 & # 57) | 2hrs 45min | 19:30 | 22:15
2024-03-02 | Jutipong Puntuleng | Complete the frontend implementation of the Reservation form page for Task 2.1.2 and 2.1.3. (#56 & # 57) | 1hr 30min | 8:30 | 10:00
2024-03-03 | Jutipong Puntuleng | Implement the ui for deleting user account for Task 4.4.3 and 4.4.4. (#120 & #121) | 2hrs | 16:30 | 18:30
2024-03-03 | Jutipong Puntuleng | Implement the ui Reservation list and put the list in its page for Task 2.2.5 (#76) | 1hr 45min | 18:30 | 20:15
2024-03-04 | Jutipong Puntuleng | Implement Reservation page that show all the detial of the reservation - related to User story 2.2 (#33) | 2hrs | 18:00 | 20:00
2024-03-05 | Jutipong Puntuleng | Modify and simplify the code of Reservation form page for Task 2.1.2 and 2.1.3. (#56 & # 57) | 2hrs | 18:00 | 20:00
2024-03-07 | Jutipong Puntuleng | Setting ci cd pipeline | 2hrs | 21:00 | 23:00
2024-03-08 | Jutipong Puntuleng | Continue setting the workflow | 3hrs | 9:00 | 12:00
2024-03-09 | Jutipong Puntuleng | Finshing setting the workflow | 3hrs 30min | 9:00 | 12:30
2024-03-09 | Jutipong Puntuleng | Start setting unit test | 3hrs | 14:30 | 17:00
2024-03-09 | Jutipong Puntuleng | Modify and Link the all Reservation page together | 3hrs | 18:30 | 21:30
2024-03-10 | Jutipong Puntuleng | Fix error in workflow and setting unit test | 3hrs 15 min | 10:30 | 13:45
2024-03-10 | Jutipong Puntuleng | Modify and Link the all Reservation page together | 2hrs 45 min | 14:30 | 17:15
2024-03-10 | Jutipong Puntuleng | Modify input validation for Reservation and Modification form | 3hrs | 19:15 | 22:10
2024-03-11 | Jutipong Puntuleng | Implement fetching vehicle data form thedatabase to ReservationFrom by get an vehicleID from vehicle page [User story 3] | 3hrs | 22:15 | 13:00:00 PM
2024-03-11 | Jutipong Puntuleng | Link data form ViewReservation to modification process. [User story 2.2 & 2.3] | 4hrs | 14:00 PM | 18:00 PM
2024-03-11 | Jutipong Puntuleng | Finishing Link data form Modification and ReserveForm to Comfirmation page.[User story 3.2] | 2hrs | 21:30 | 23:30
Sprint 3
Date | Members name | Task | Hour spent | Start time | End time
2024-03-12 | Jutipong Puntuleng | Start creating wireframe for Check In form [User Story 8: Task 8.1.1 (#207)] | 30 min | 23:00 | 11:30
2024-03-12 | Jutipong Puntuleng | Fixing the error and bug on admin dashboard | 3hrs 30min | 12:45 | 16:15
2024-03-12 | Jutipong Puntuleng | Update Unit test | 1 hrs 45 min | 21:00 | 22:45
2024-03-12 | Jutipong Puntuleng | Create Check In page and Implement Rental Agreement page [User Story 8: Task 8.1.4 (#210)] | 50 min | 22:45 | 23:35
2024-03-12 | Jutipong Puntuleng | Link Check In page and Rental Agreement together [User Story 8: Task 8.4.1 & 8.4.2 (#222 & #223)] | 5 min | 23:35 | 23:40
2024-03-12 | Jutipong Puntuleng | Create comformation message when submit the Rental Agreement form [ User Story 8: Task 8.4.3 (#224)] | 5 min | 23:40 | 23:45
2024-03-12 | Jutipong Puntuleng | Implement Check In form [User Story 8: Task 8.1.4 (#210)] | 15 min | 23:45 | 0:00
2024-03-13 | Jutipong Puntuleng | Implement Check In form [User Story 8: Task 8.1.4 (#210)] | 30 min | 12:00 | 0:30
2024-03-13 | Jutipong Puntuleng | Modify admin dashboard by adjust the style, remove unecessary thing and add missing input field | 2 hrs 30 min | 11:00 | 14:30
2024-03-13 | Jutipong Puntuleng | Update Unit test | 2 hrs | 14:45 | 16:45
2024-03-13 | Jutipong Puntuleng | Fix vercel bug and improve workflow speed. | 1 hr 45 min | 21:00 | 22:45
2024-03-17 | Jutipong Puntuleng | Modify Check process and rental agreement. [User Story 8 (#206)] | 4 hrs | 12:00 | 16:00
2024-03-17 | Jutipong Puntuleng | Refactor Reservation Form [User Story 2.1 (#16)] | 2 hrs | 16:30 | 18:30
2024-03-18 | Jutipong Puntuleng | Modify Reservation card on admin side. [User Story 6.2 (#42)] | 1 hrs | 11:00 | 12:00
2024-03-18 | Jutipong Puntuleng | Refactor Reservation Process [User Story 2.1 (#16)] | 4 hrs | 12:00 | 15:00 PM
2024-03-18 | Jutipong Puntuleng | Refactor view ReservationList Page [User Story 2.2 (#33)] | 2 hrs | 16:00 PM | 18::00 PM
2024-03-19 | Jutipong Puntuleng | Refactor view ReservationList Page [User Story 2.2 (#33)] | 2 hrs | 11:30 | 13:30
2024-03-19 | Jutipong Puntuleng | Refactor view Profile Page | 2 hrs | 14:00 | 16:00
2024-03-19 | Jutipong Puntuleng | Edit database and logic for User and Reservation | 2 hrs 30 min | 16:00 | 18:30
2024-03-21 | Jutipong Puntuleng | Refactor Confirmation Page [User Story 2.4 (#29)] | 4 hrs | 11:00 | 15:00
2024-03-21 | Jutipong Puntuleng | Refactor Confirmation Page [User Story 2.4 (#29)] | 1 hrs | 19:00 | 20:00
2024-03-22 | Jutipong Puntuleng | Refactor view Reservation Detail Page [User Story 2.2 (#33)] | 3 hrs | 10:30 | 13:30
2024-03-22 | Jutipong Puntuleng | Modify Reservation card on admin side to change change button when status change | 45 min | 14:00 | 14:45
2024-03-23 | Jutipong Puntuleng | Modify Check in process and rental agreement [User Story 8 (#206)] | 4 hrs 15 min | 11:30 | 15:45
2024-03-23 | Jutipong Puntuleng | Refactor Modify Reservation [User Story 2.3 (#28)] | 2 hrs | 16:00 | 18:00
2024-03-23 | Jutipong Puntuleng | Mofidy database and logic for reservation [User Story 2 (#15)] | 2 hrs | 19:00 | 21:00
2024-03-24 | Jutipong Puntuleng | Modify Check in process. [User Story 8 (#206)] | 2 hrs | 10:30 | 12:30
2024-03-24 | Jutipong Puntuleng | Modify rental agreement pdf. [User Story 8 (#206)] | 4 hrs | 15:00 | 19:00
2024-03-24 | Jutipong Puntuleng | Fixing workflow Error | 4 hrs | 22:00 | 2:00
2024-03-25 | Jutipong Puntuleng | Update Unit test
2024-03-25 | Jutipong Puntuleng | Upload E2E

## Ryan Mazari
Sprint 1
Date | Members name | Task | Hour spent | Start time | End time
2024-02-07 | Ryan Mazari | Brainstorming User Stories (how to divide them, which order to list them) | 4hrs | 16:00 | 20:00
2024-02-08 | Ryan Mazari | Wrote 6 user stories | 6hrs | 18:00 | 0:00
2024-02-09 | Ryan Mazari | Redid the user stories in accordance to Lecture Week 4 before Lab Session on Friday | 3hrs | 11:00 | 14:00
2024-02-10 | Ryan Mazari | After receiving feebacks during Lab Session, had to again modify user stories | 4hrs | 19:00 | 23:00
2024-02-11 | Ryan Mazari | Continued writing user stories + linked them to tasks | 5hrs | 17:00 | 22:00
2024-02-12 | Ryan Mazari | Finished user stories, only linked user stories to tasks | 2hrs | 20:00 | 22:00
Sprint 2
Date | Members name | Task | Hour spent | Start time | End time
26/02/2024 | Ryan Mazari | Lean MongoDB and Next JS basic concepts, and began to set up MongoDB databse | 2.5 hours | 7:00 | 9:00
27/02/2024 | Ryan Mazari | Setting up Database MongoDB for TASK 2.2.3 and TASK 2.2.4 | 2 hours | 8:30 | 10:30
2024-06-03 | Ryan Mazari | Tried to integrate calender API for date selection using Google Calendar API | 3 hours | 13:00 | 16:00
2024-06-03 | Ryan Mazari | Converted user story to tasks for user story 9.1 | 1.5 hours | 9:00 | 10:30
2024-07-03 | Ryan Mazari | Wrote 2 acceptance tests for create customer account and delete reservation | 1 hour | 10:00 | 11:00
2024-08-03 | Ryan Mazari | Implementing home page based on wireframe | 1.5 hours | 11:00 | 12:30
2024-08-03 | Ryan Mazari | Continued to implement the home page and creating the logo | 2 hours | 23:00 | 1:00
2024-09-03 | Ryan Mazari | Styled the login page and incoporated navbar for the user to come back once loged in using Tailwind | 1.5 hours | 21:30 | 23:00
2024-10-03 | Ryan Mazari | Styled the sign up page using Tailwind and fixed small bugs | 2 hours | 23:00 | 13:00
2024-10-03 | Ryan Mazari | Tried to add the name of the user when signed in to the navbar but encountered issues. Instead I want to display the email address which is easier to do. | 3 hours | 20:00 | 23:00
2024-11-03 | Ryan Mazari | Worked on sprint 3 tasks description | 1 hour | 20:00 | 21:00
Sprint 3
Date | Members name | Task | Hour spent | Start time | End time
18/03/2024 | Ryan Mazari | Sprint 3 Planning that was not done, have now been done. | 3 hrs | 7:00 | 10:00
19/03/2024 | Ryan Mazari | Started writing user stories for sprint 4 (Review and Rating + Interactive Map) | 2 hrs | 8:30 | 10:30
20/03/2024 | Ryan Mazari | Finished writing user sotries and started writing tasks for specicifc user stories | 3 hrs | 13:00 | 16:00
22/03/2024 | Ryan Mazari | Finished writing tasks for each user stories and assigned them to team members | 2 hrs | 9:00 | 11:00
23/03/2024 | Ryan Mazari | Started and finished completely Sprint 4 Planning for the whole team with justification for priority and risk | 3 hrs | 5:00 | 8:00
24/03/2024 | Ryan Mazari | Started and completed sequence + activity diagram for user stories 1 to 5 | 3.5 hrs | 21:00 | 12:30
24/03/2024 | Ryan Mazari | Started and completed sequence + activity diagram for user stories 6 to 9 | 4 hrs | 6:00 | 10:00